## Sheet1
Activity Number | Activity Title | Discipline | Start Date | End Date | Duration (days) | Physical Progress | Status | Category | Comment JDate | Issued JDate | Responsible | plan | Plan
85205-AHC-CV-DW-2007 | Road plan and details for booster pump station | Civil | 2025-06-02 | 2025-07-16 | 44 | 74 | Approved | Drawing |  |  | Contractor (Waiting for First Issue) | خانم مهندس مرجوعی مسئول بخش سیویل هستند و در حال حاضر در پروژه دهاقان فعالیت دارند
85205-AH1-CV-DW-2005 | Road Plan ,Route & Details | Civil | 2025-07-03 | 2025-07-09 | 6 | 100 | Finished | Drawing | 1403/03/20 | 1403/02/29 | Contractor (Waiting For new Issue or Reply) | امروز ارسال شد | sghhhhhhl
85205-AH2-CV-DW-2009 | Road Plan & Details | Civil |  |  |  | 14 | Commented | Drawing | 1403/10/01 | 1403/09/13 | Contractor (Waiting For new Issue or Reply) | خانم مهندس مرجوعی مسئول بخش سیویل هستند و در حال حاضر در پروژه دهاقان فعالیت دارند
85205-AH2-CV-DW-2011 | Finish Grading & Surface Drainage System Plan & Details | Civil |  |  |  | 80 | Reject | Drawing | 1403/10/01 | 1403/09/17 | Contractor (Waiting For new Issue or Reply) | خانم مهندس مرجوعی مسئول بخش سیویل هستند و در حال حاضر در پروژه دهاقان فعالیت دارند
85205-AH2-CV-DW-2010 | Paving Plan & Details | Civil |  |  |  | 81 | Reject | Drawing | 1403/10/09 | 1403/09/19 | Contractor (Waiting For new Issue or Reply) | خانم مهندس مرجوعی مسئول بخش سیویل هستند و در حال حاضر در پروژه دهاقان فعالیت دارند
85205-AH2-CV-DW-2002 | Surface Drainage System Plan & Details | Civil |  |  |  | 97 | Reject | Drawing | 1403/10/09 | 1403/09/27 | Contractor (Waiting For new Issue or Reply) | خانم مهندس مرجوعی مسئول بخش سیویل هستند و در حال حاضر در پروژه دهاقان فعالیت دارند
85205-AHC-CV-DW-2005 | Road Plan ,Route & Details | Civil |  |  |  | 86 | Approved | Drawing | 1404/01/30 | 1403/12/21 | Contractor (Waiting For new Issue or Reply) | مدرک کلاس 1 میباشد , لذا منتظر اعمال نظر کارفرما هستیم
85205-AH1-CV-DW-2007 | Rough Grading Plan & Details | Civil |  |  |  | 4 | Commented | Drawing | 1404/02/28 | 1404/02/09 | Contractor (Waiting For new Issue or Reply) | در انتظار پاسخ مدیر پروژه و کارفرما جهت شفاف سازی محدوده های کاری مطابق ایمیل ارسال شده توسط بخش سیویل در تاریخ 1404/03/05
85205-AH1-CV-DW-2008 | Finish Grading Plan & Details | Civil |  |  |  | 78 | Commented | Drawing | 1404/02/27 | 1404/02/09 | Contractor (Waiting For new Issue or Reply) | در انتظار پاسخ مدیر پروژه و کارفرما جهت شفاف سازی محدوده های کاری مطابق ایمیل ارسال شده توسط بخش سیویل در تاریخ 1404/03/05
85205-AH1-CV-DW-2002 | Finish Grading & Surface Drainage System Plan & Details | Civil |  |  |  | 32 | Commented | Drawing | 1404/02/28 | 1404/02/09 | Contractor (Waiting For new Issue or Reply) | در انتظار پاسخ مدیر پروژه و کارفرما جهت شفاف سازی محدوده های کاری مطابق ایمیل ارسال شده توسط بخش سیویل در تاریخ 1404/03/05
85205-AHC-CV-DW-2001 | Surface Drainage System Plan & Details | Civil |  |  |  | 36 | Approved | Drawing | 1404/03/17 | 1404/03/04 | Contractor (Waiting For new Issue or Reply) | امروز ارسال شد
85205-AH2-EL-LI-2001 | List for Conductor and Shieldwire Stringing Tables Korait - Ahvaz I Desalting (11kV-2C Transmission Line) | Electrical |  |  |  | 92 | Approved With Comment | List | 1403/12/19 | 1403/11/28 | Contractor (Waiting For new Issue or Reply) | امروز ارسال میشود.
85205-AHC-EL-MR-2414 | Material Requisition for Lighting Poles and Towers | Electrical |  |  |  | 4 | Approved | Material Requisition | 1404/02/10 | 1404/01/24 | Contractor (Waiting For new Issue or Reply) | امروز ارسال میشود.
85205-AHC-GE-RP-2001 | SCOPE OF WORK CLARIFICATION | General | 2025-07-02 | 2025-07-10 | 8 | 80 | Approved with Comments | REPORT | 1403/02/02 | 1402/12/09 | Contractor (Waiting For new Issue or Reply)
85205-000-GE-LI-2003 | Document List | General | 2025-07-03 | 2025-07-16 | 13 | 100 | Finished | List | 1403/07/17 | 1403/06/20 | Contractor (Waiting For new Issue or Reply)
85205-AHC-GE-DW-2002 | Green area Plan | General |  |  |  | 6 | Commented | Drawing | 1404/03/13 | 1404/02/28 | Contractor (Waiting For new Issue or Reply)
85205-000-HV-DS-2005 | Data Sheet for HVAC Main Equipment for Administration Building | HVAC |  |  |  | 0 | Commented | Data Sheet | 1404/01/10 | 1403/10/22 | Contractor (Waiting For new Issue or Reply)
85205-000-HV-LY-2001 | HVAC System layout for Administration Building | HVAC |  |  |  | 45 | Commented | Layout | 1404/01/10 | 1403/10/22 | Contractor (Waiting For new Issue or Reply)
85205-000-HV-MR-2007 | MRQ for HVAC Main Equipment for Administration Building | HVAC |  |  |  | 16 | Commented | Material Requisition | 1404/01/10 | 1403/10/22 | Contractor (Waiting For new Issue or Reply)
85205-000-HV-MT-2006 | MTO for HVAC & Plumbing Accessories for Administration Building | HVAC |  |  |  | 30 | Commented | Material Take Off | 1404/02/01 | 1403/10/22 | Contractor (Waiting For new Issue or Reply)
85205-000-HV-CN-2004 | HVAC and Plumbing Load Calculation for Administration Building | HVAC |  |  |  | 80 | Approved | Calculation | 1404/03/11 | 1404/02/20 | Contractor (Waiting For new Issue or Reply)
85205-AH2-IN-DG-2001 | Loop Diagrams (DCS, ESD, F&G) | Instrument |  |  |  | 37 |  | Diagram |  |  | Contractor (Waiting for First Issue) | 1404/04/31
85205-AH1-IN-LI-2005 | I/O List for ESD System (IF ANY) | Instrument |  |  |  | 65 |  | List |  |  | Contractor (Waiting for First Issue) | 1404/04/31
85205-AP7-IN-LY-2001 | Instrumentaion and Control Panel Location Layout | Instrument |  |  |  | 2 | Commented | Layout | 1403/07/30 | 1403/07/03 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AH1-IN-DG-2001 | Loop Diagrams (DCS, ESD, F&G) | Instrument |  |  |  | 56 | Commented | Diagram | 1403/07/25 | 1403/07/03 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AHC-IN-DG-2005 | Loop Diagrams (DCS, ESD, F&G) | Instrument |  |  |  | 36 | Commented | Diagram | 1403/07/25 | 1403/07/03 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AP7-IN-MT-2001 | M.T.O. of for BULK material | Instrument |  |  |  | 64 | Approved With Comment | Material Take Off | 1403/07/30 | 1403/07/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/28
85205-AP1-IN-MT-2001 | M.T.O. of for BULK material | Instrument |  |  |  | 73 | Approved With Comment | Material Take Off | 1403/07/30 | 1403/07/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/28
85205-AHC-IN-MT-2001 | M.T.O. of for BULK material | Instrument |  |  |  | 47 | Approved With Comment | Material Take Off | 1403/08/07 | 1403/07/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/28
85205-AH1-IN-MT-2001 | M.T.O. of for BULK material | Instrument |  |  |  | 55 | Approved With Comment | Material Take Off | 1403/08/07 | 1403/07/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/28
85205-000-IN-MR-2007 | Material Requisition for Instrument Bulk Materials | Instrument |  |  |  | 35 | Commented | Material Requisition | 1403/08/07 | 1403/07/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/29
85205-000-IN-MR-2005 | Material Requisition for Junction Boxes & Glands | Instrument |  |  |  | 65 | Commented | Material Requisition | 1403/08/07 | 1403/07/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/29
85205-AH1-IN-DG-2003 | Logic Diagrams (DCS, ESD, F&G) | Instrument |  |  |  | 71 | Commented | Diagram | 1403/09/10 | 1403/08/16 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AHC-IN-DG-2004 | Logic Diagrams (DCS, ESD, F&G) | Instrument |  |  |  | 6 | Commented | Diagram | 1403/09/10 | 1403/08/16 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AP7-IN-DG-2005 | Junction Box Terminal Wiring Diagram | Instrument |  |  |  | 18 | Reject | Diagram | 1403/08/28 | 1403/08/21 | Contractor (Waiting For new Issue or Reply) | 1404/04/19
85205-000-IN-LY-2001 | PA/GA & LAN/WAN & CCTV Layout for Administration Building | Instrument |  |  |  | 62 | Commented | Layout | 1403/11/23 | 1403/11/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AH2-IN-MT-2001 | M.T.O. of for BULK Material | Instrument |  |  |  | 96 | Approved With Comment | Material Take Off | 1403/12/07 | 1403/11/28 | Contractor (Waiting For new Issue or Reply) | 1404/04/28
85205-000-IN-LY-2002 | PA/GA & LAN/WAN & CCTV Layout for Guard House | Instrument |  |  |  | 5 | Approved With Comment | Layout | 1404/01/17 | 1403/12/08 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AH1-IN-RP-2001 | Existing Instrumentation & Control System REPORT | Instrument |  |  |  | 53 | Reject | REPORT | 1403/12/25 | 1403/12/18 | Contractor (Waiting For new Issue or Reply) | 1404/04/26
85205-AH2-IN-RP-2001 | Existing Instrumentation & Control System REPORT | Instrument |  |  |  | 47 | Reject | REPORT | 1404/01/17 | 1403/12/18 | Contractor (Waiting For new Issue or Reply) | 1404/04/26
85205-AHC-IN-RP-2001 | Existing Instrumentation & Control System REPORT | Instrument |  |  |  | 91 | Reject | REPORT | 1403/12/26 | 1403/12/18 | Contractor (Waiting For new Issue or Reply) | 1404/04/26
85205-AP1-IN-RP-2001 | Existing Instrumentation & Control System REPORT | Instrument |  |  |  | 21 | Reject | REPORT | 1403/12/26 | 1403/12/18 | Contractor (Waiting For new Issue or Reply) | 1404/04/26
85205-AP7-IN-RP-2001 | Existing Instrumentation & Control System REPORT | Instrument |  |  |  | 29 | Reject | REPORT | 1403/12/26 | 1403/12/18 | Contractor (Waiting For new Issue or Reply) | 1404/04/26
85205-AHC-IN-DG-2001 | Instrument and Electrical Interconnection Diagrams | Instrument |  |  |  | 51 | Approved | Diagram | 1404/02/27 | 1404/02/06 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-000-IN-MR-2004 | Material Requisition for Instrument Cables | Instrument |  |  |  | 55 | Approved | Material Requisition | 1404/03/05 | 1404/02/17 | Contractor (Waiting For new Issue or Reply) | 1404/04/19
85205-AH1-IN-LI-2002 | Instrument Cable Schedule | Instrument |  |  |  | 13 | Approved | List | 1404/03/03 | 1404/02/17 | Contractor (Waiting For new Issue or Reply) | 1404/04/18
85205-AH2-IN-LI-2002 | Instrument Cable Schedule | Instrument |  |  |  | 34 | Approved | List | 1404/03/05 | 1404/02/17 | Contractor (Waiting For new Issue or Reply) | 1404/04/18
85205-AHC-IN-LI-2005 | Instrument Cable Schedule | Instrument |  |  |  | 28 | Approved | List | 1404/03/05 | 1404/02/17 | Contractor (Waiting For new Issue or Reply) | 1404/04/18
85205-AP1-IN-LI-2002 | Instrument Cable Schedule | Instrument |  |  |  | 69 | Approved | List | 1404/03/05 | 1404/02/17 | Contractor (Waiting For new Issue or Reply) | 1404/04/18
85205-AP7-IN-LI-2001 | Instrument Cable Schedule | Instrument |  |  |  | 54 | Approved | List | 1404/03/05 | 1404/02/17 | Contractor (Waiting For new Issue or Reply) | 1404/04/18
85205-AH1-IN-DG-2002 | Junction Box Terminal Wiring Diagram (DCS, ESD, F&G) | Instrument |  |  |  | 67 | Approved | Diagram | 1404/03/11 | 1404/02/21 | Contractor (Waiting For new Issue or Reply) | 1404/04/19
85205-AH1-IN-DG-2004 | Instrument Cable Route | Instrument |  |  |  | 18 | Reject | Diagram | 1404/03/13 | 1404/02/30 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AP1-IN-DG-2001 | Instrument Cable Route | Instrument |  |  |  | 1 | Reject | Diagram | 1404/03/13 | 1404/02/30 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-000-IN-MR-2002 | Material Requisition for F&G System & Detectors | Instrument |  |  |  | 39 | Commented | Material Requisition | 1404/03/12 | 1404/02/31 | Contractor (Waiting For new Issue or Reply) | 1404/04/19
85205-AH2-IN-DG-2002 | Instrument Cable Route | Instrument |  |  |  | 7 | Commented | Diagram | 1404/03/18 | 1404/02/31 | Contractor (Waiting For new Issue or Reply) | 1404/04/31
85205-AHC-IN-LY-2001 | Instrument & JB Location Layout | Instrument |  |  |  | 66 | Commented | Layout | 1404/03/15 | 1404/03/06 | Contractor (Waiting For new Issue or Reply) | 1404/04/26
85205-000-PI-MT-2011 | Material Take Off for Non-Metal Piping | Piping |  |  |  | 9 | Approved With Comment | Material Take Off | 1404/03/07 | 1404/02/16 | Contractor (Waiting For new Issue or Reply) | ارسال شد.
85205-AH2-SA-CE-2003 | F&G Cause and Effect for Process Area (AH2-PU) | Safety |  |  |  | 15 | Approved With Comment | Cause & Effect Diagram | 1403/09/12 | 1403/07/08 | Contractor (Waiting For new Issue or Reply) | 1404/04/21
85205-AH1-SA-CE-2005 | F&G Cause and Effect for Process Area (AH1-PU) | Safety |  |  |  | 64 | Approved With Comment | Cause & Effect Diagram | 1403/09/12 | 1403/07/09 | Contractor (Waiting For new Issue or Reply) | 1404/04/14
85205-AH1-SA-CE-2002 | F&G Cause and Effect for Buildings (AH1-DE) | Safety |  |  |  | 94 | Approved | Cause & Effect Diagram | 1404/02/23 | 1404/01/27 | Contractor (Waiting For new Issue or Reply) | پس از ارسال کامنت شیت، نسخه نهایی ارسال می گردد.
85205-AH1-SA-CE-2006 | F&G Cause and Effect for Buildings (AH1-PU) | Safety |  |  |  | 13 | Approved | Cause & Effect Diagram | 1404/02/20 | 1404/02/06 | Contractor (Waiting For new Issue or Reply) | منتظر اعلام نظر کارفرما هستیم.
85205-AHC-ST-CN-2007 | Calculation Note for Pump-EVAPORATION POUND PUMP Foundation | Structure |  |  |  | 48 |  | Calculation |  |  | Contractor (Waiting for First Issue) | 1404/04/26
85205-AHC-ST-DW-2701 | Foundation Details and Drawing for EVAPORATION POUND PUMP | Structure |  |  |  | 83 |  | Drawing |  |  | Contractor (Waiting for First Issue) | 1404/04/26
85205-AHC-ST-CN-2008 | Calculation note for OWS pump foundation/structure | Structure |  |  |  | 22 |  | Calculation |  |  | Contractor (Waiting for First Issue) | درخواست شماره مدرک به کارفرما داده شده بود که هنوز پاسخی داده نشده است
85205-AHC-ST-DW-2012 | Foundation/Structural details and drawing for OWS pump | Structure |  |  |  | 90 |  | Drawing |  |  | Contractor (Waiting for First Issue) | درخواست شماره مدرک به کارفرما داده شده بود که هنوز پاسخی داده نشده است
85205-AH1-ST-CN-2009 | Calculation note for recycle pump foundation | Structure |  |  |  | 73 |  | Calculation |  |  | Contractor (Waiting for First Issue) | 1404/04/18
85205-AH1-ST-DW-2008 | Foundation details and drawing for recycle pump | Structure |  |  |  | 20 |  | Drawing |  |  | Contractor (Waiting for First Issue) | 1404/04/18
85205-AH2-ST-DW-2001 | Foundation & Structure drawing for Bridges 1,2,3,4 for 16" & 12" Pipe line (AH2-AH4) | Structure |  |  |  | 2 | Commented | Drawing | 1403/12/22 | 1403/12/07 | Contractor (Waiting For new Issue or Reply)
85205-AHC-ST-CN-2002 | Calculation Note for Pump-6014 A/B/C/D Foundation | Structure |  |  |  | 95 | Commented | Calculation | 1404/03/18 | 1404/03/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/11
85205-AHC-ST-DW-2002 | Foundation Details and Drawing for Pump-6014 A/B/C/D | Structure |  |  |  | 46 | Commented | Drawing | 1404/03/18 | 1404/03/07 | Contractor (Waiting For new Issue or Reply) | 1404/04/11